## POC
PoC development cost		2017			2018
		Oct	Nov	Dec	Jan	Feb	Mar	Apr	May	Jun	Jul	Aug	Sep	Oct	Nov	Dec
Microscope with AI solution
Mechanical	Time	40	8
	Investment	80000	20000
Electrical	Time	40	40
	Investment	80000	20000
Software (including deep learning algorithm collection)	Time	120	120	120	120	120
	Investment	200000	200000	200000	200000	200000
Optical	Time	80	40
	Investment	50000	50000
Microfluid transfer system	Time	40	120	120	120
	Investment	200000	150000	150000	150000
Clinical validation and testing	Time		240	240	240	240
	Investment		100000	100000	100000	100000
		320	568	480	480	360	0	0	0	0	0	0	0	0	0	0	2208
		610000	540000	450000	450000	300000	0	0	0	0	0	0	0	0	0	0	2350000
		610000	1150000	1600000	2050000	2350000	2350000	2350000	2350000	2350000	2350000	2350000	2350000	2350000	2350000	2350000
RDT tester Solution
Mechanical	Time			40	40
	Investment			80000	80000
Electrical	Time			40	40
	Investment			80000	20000
Software	Time			120	120	120
	Investment			50000	50000	50000
Optical	Time			80	40
	Investment			4000	4000
Microfluid transfer system	Time			8	240	240	240	240
	Investment				150000	150000	150000	150000
Container management system	Time				120	120	120	120
	Investment				200000	200000	200000	200000
RDT Kit management system	Time				120	120	120	120
	Investment				200000	200000	200000	200000
Clinical validation and testing	Time						240	240
	Investment						100000	100000
RDT Kits	Time
	Investment				200000
		0	0	288	720	600	960	960	0	0	0	0	0	0	0	0	3528
		0	0	214000	904000	600000	750000	750000	0	0	0	0	0	0	0	0	3218000

Microfluid Lab-on-chip solution
Mechanical	Time					60	60
	Investment					40000	40000
Electrical	Time					60	60
	Investment					40000	40000
Software	Time									240	240
	Investment									200000	200000
Lab-on-chip (Outsource)	Time
	Investment							2000000	2000000	2000000	2000000
Microfluid transfer system	Time							240	240
	Investment							150000	150000	400000	400000
Clinical validation and testing	Time									240	240	240	240
	Investment									100000	100000	100000	100000
		0	0	0	0	120	120	240	240	480	720	240	240	240	0	0	2640
		0	0	0	0	80000	80000	2150000	2150000	2800000	2900000	100000	100000	100000	0	0	10460000

Vitals measurement solution
Mechanical	Time							60	120	120
	Investment							150000	150000	150000
Electrical	Time							60	120	120
	Investment							150000	150000	150000
Software	Time									240	240	240
	Investment									200000	200000	200000
Optical	Time							60	120	120
	Investment							150000	150000	150000
Sensors	Time							60	120	120
	Investment							150000	150000	150000
Clinical validation and testing	Time									240	240	240	240
	Investment									200000	200000	200000	200000
		0	0	0	0	0	0	240	480	480	240	480	480	240	240	0	2880
		0	0	0	0	0	0	600000	600000	600000	200000	400000	400000	200000	200000	0	3200000
										11256
Technology										19228000
Consultation fees					400000	400000	400000	400000	400000	400000	400000	400000	4800000
Usability design		800000	800000	800000	800000	800000	800000	800000	800000					8000000
Patent				1000000						1000000
Adminstrative		400000	400000	400000	400000	400000	400000	400000	400000	6000000
Total										39028000
		1810000	1740000	2864000	2954000	2580000	2430000	5100000	4350000	5000000	4700000	1300000	1300000	1100000	1000000	800000

## BOM
Example bill of materials (Microscope)
ITEM	COST
REES52 FT232RL USB TO TTL 5V 3.3V Download Cable To Serial Adapter Module for Arduino	320
Klera's Labeled 18 Values Ultimate Capacitor Kit Pack of 555 Pcs	549
LM2596 Voltage Regulator + LED Voltmeter DC Buck Step Down Converter Module	496
2 of Invento 8944130044485 1 Pieces Mechanical Endstop Switch Reprap Mendel Prusa Ramps V1.4 for 3D Printer or CNC	250
Invento LM8UU_1 2 Pieces Lm8Uu 8mm Linear Bush Ball Bearing for Reprap Prusa 3D Printer or CNC or Robotic	370
2pcs EN31 Smooth Rod 8mm OD, long 300 mm (0.3mtr) for Bearing- DIY Projects	250
2 of Flexible Coupling Shaft Coupler 5mm to 8mm for 3D Printer and CNC (Quantity: 1 pc)	215
Tfpro Aluminium Soldering Wire 1mm 50gm Roll	208
Stanley 69-031B Round 30-Watt Corded Soldering Iron, Black and Chrome	299
Generic Elementz High Quality Nickel Plated 840 Points Bread Board or Solderless Piecesb Circuit Test Board, White	139
Robo India R-PACK Resistance Pack, 20 Type, 25 Each, - 500 Pieces	350
Arduino UNO R3 board with DIP Atmega328P	1523
ClassyTek Hi-Speed USB 2.0 Type A Male to B Male 1.5 Meter Printer Scanner Cable – Black	249
Assembled Pi T-Cobbler Plus - GPIO Breakout - for RasPi A+/B+/Pi 2/Pi 3	799
M069 16 Bit I2C ADS1115 Module ADC 4 channel with Pro Gain Amplifier for Arduino	599
Quad Store(TM) - Ultra kit for Raspberry Pi 3 Model B and 2 (Without Raspberry)	3801
Raspberry Pi NoIR Camera Module V2 - 8MP 1080P30	2049
Raspberry Pi 3 Model B 1 GB RAM 1.2 GHz 64-bit Quad core ARM CPU with 802.11n wifi and bluetooth -The Complete Kit (With Black Case LW)	4699
OpenBeam Shaft clamp (4p, 2p) for OpenBeam, MakerBeam 300mm, linear slide rail and carriage, MakerBeamXL MakerBeamXL Starter Kit Black Premium	29747
Solder Leaded - 15-gram Tube	700
MakerBeam NEMA 17 Bracket For Stepper Motor	900
Hakko Soldering Iron - 40W 230V EU Plug	650
MakerBeamXL Starter Kit - Black Anodised Threaded	16485
L4940V5 - Fixed LDO Voltage Regulator, 7V to 17V, 500mV Dropout, 5Vout, 1.5Aout, TO-220-3	234.36
SN754410NE - Peripheral Driver, Line, 4 Outputs, 4.5 V to 36 V supply, 39 V/2 A out, DIP-16	182.95
L293DD013TR - MOTOR DRIVER, DC, STEPPER, 0.6A, SOIC-20	1285
356 - TRIM POTENTIOMETER, PROTOTYPING BOARD	216
SN74HC595N - 8bit Shift Register with 3 State Output Registers in DIP-16 Package	172.36
PN2222ATA - Bipolar (BJT) Single Transistor, NPN, 40 V, 300 MHz, 625 mW, 1 A, 300 hFE	57.4
1N4004 - Standard Recovery Diode, 400 V, 1 A, Single, 1.1 V, 30 A	24.6
Adafruit Motor/Stepper/Servo Shield for Arduino	1851.42
3.6 kg cm CAPTIVE LINEAR ACTUATOR STEPPER MOTOR (1.68 Amp Motor) PITCH - M8x1.25 WITH 250 MM LEAD SCREW	4491.08
NEMA 17(42MM) MOUNTING BRACKET	667.88
2 Amp (12 VOLTS DC) POWERSUPPLY (Transformer), 2 Amp Bipolar Microstepping Drive	4827.38
Jumper Wires Standard 7" M/M Pack of 30, SparkFun IR Thermometer Evaluation Board - MLX90614	6030.36
MKII Robotic Claw with Servo, Dagu-Rs026	3822.47
Stepper motor - NEMA-17 size - 200 steps/rev, 12V 350mA, Motor/Stepper/Servo Shield for Arduino v2 Kit – v2.3	4196
27:1 Planetary Gearbox Nema 17 Stepper Motor DIY CNC Hobby Camera Robotics	7618
MagiDeal Pack of 10PCS Lightweight Corrosion Resistant Stainless Steel Nuts Bolts Screws Thread Hexagon Fastener M2	290
Magideal 100Pcs Stainless Steel Screws Button Head Socket Allen Cap Bolts M2*12 mm	600
Anti-Backlash Nut Block for 8mm Metric Acme Lead Screw, M3 - Socket Head Screw (10 pcs), M3 - Socket Head Screw (10 pcs), M8 - Hex Nut, 8mm Metric Acme Lead Screw / 8mm Metric Acme Lead Screw	3598.52
Hex Nut M3, M4, M5, M6, M8, M10 - Size : M6, Allen Key set, Hex Nut M3, M4, M5, M6, M8, M10 - Size : M8, Washer/Shim M3, M4, M5, M6, M8, M10 - Size : M6, Washer/Shim M3, M4, M5, M6, M8, M10 - Size : M8, Washer/Shim M3, M4, M5, M6, M8, M10 - Size : M3, M2 Bolt - Length : 15 mm	268.84
3D print, mechanical	3099
3D print, optical	3097
Bi-convex Biconvex Lens Set 25mm Diameter 40mm Focal Length for Google Cardboard	1779
Adafruit Accessories Flex Cable for Raspberry Pi Camera - 1 meter 1 piece	1828
AmScope PA4X 4X Plan Achromatic Microscope Objective	4421
2pcs M6 6mm SS304 Threaded rods 300mm (0.3mtr) Long	250
2pcs M8 8mm SS304 Threaded rods 300mm (0.3mtr) Long	250
MagiDeal Pack of 10PCS Lightweight Corrosion Resistant Stainless Steel Nuts Bolts Screws Thread Hexagon Fastener M2	290
Magideal 100Pcs Stainless Steel Screws Button Head Socket Allen Cap Bolts M2*12 mm	600
27:1 Planetary Gearbox Nema 17 Stepper Motor DIY CNC Hobby Camera Robotics	7618
5.5 kg cm BIPOLAR STEPPER MOTOR (1.5 Amp Motor) Fitted With Connector, / 2 Amp Bipolar Microstepping Drive, 2 Amp (12 VOLTS DC) POWERSUPPLY (Transformer)	5920.06
AccuChek Safe-T-Pro-Uno Lancing Devices (Single Use) - Pack of 20 Pcs.	240
1x TR FASTENINGS M2- FABRWAN100- Washer, Plain, Form A, Brass, Nickel Plated, M2, Pack of 100	648.61
Esaw Slide Box of 50 Prepared Slides	1299
Recombigen Clear Scan Rapid Malaria test Pack of 40	1500
Urine Strip Urisign 4H Glucose, Ketone, Protein, pH - 300 Strip (pack of 3)	3350
Washer/Shim M3, M4, M5, M6, M8, M10 - Size : M6	577.94
Olympus 40X Infinity Plan Achromat Objective for CX-21i	7487
Jainco 5022 100X Microscope Objective Lens	1332
IB Basics SS Hex Nut 202Q Diameter M6	170
Quality lens, biconvex, AR coated 630-1100nm	6441.77
OMAX 0. 01mm Microscope Camera Calibration Slide (Stage Micrometer)	1754
White 144 PCS Adjustable LED Ring Light for Stereo Microscope & Camera, with Power Adapter	3929
ESAW BRASS MECHANICAL STAGE WITH MARKINGS FOR STUDENT;MEDICAL MICROSCOPES	999

	164962